## Dashboard
ADMITFLOW ¦ PLANNED WORK DISTRIBUTION
Task IDs, workstreams, owners and planned hours follow the supplied allocation. Dates, dependencies and task-level status are not recorded in that plan.
PROJECT SNAPSHOT
Planned tasks |  |  |  | Total planned hours
Actual hours recorded |  |  |  | Task statuses recorded
OWNER DISTRIBUTION |  |  |  | PHASE EFFORT
Owner | Task Count | Planned Hours | Source | Phase Order | Phase | Planned Hours | Task Count
Zahir |  |  | Supplied distribution | 1 | Foundation
Samiksha |  |  | Supplied distribution | 2 | Planning
Both |  |  | Supplied distribution | 3 | Requirements
|  |  |  | 4 | Data
|  |  |  | 5 | Analytics
|  |  |  | 6 | ML
|  |  |  | 7 | Backend
|  |  |  | 8 | Frontend
|  |  |  | 9 | Engineering
|  |  |  | 10 | Deployment
|  |  |  | 11 | Documentation
|  |  |  | 12 | Black Book
|  |  |  | 13 | QA
|  |  |  | 14 | Demo
|  |  |  | 15 | Final
SOURCE AND STATUS NOTES
The supplied allocation records planned work only. Dates from 25-Sep-2026 through 03-Oct-2026 are illustrative schedule placeholders, not actual historical work dates. Task-level completion, dependencies, actual hours and outcomes remain unrecorded. Confirm each student's contribution before submission.
KNOWN LIMITATIONS
Synthetic data; weak classifier results; six annual observations in the forecast; assumption-driven scenarios; process-local audit log; build-size warning. Docker/CI/CD/live deployment and stakeholder study tasks are not verified as complete.

## Master Tracker
Task ID | Phase Order | Phase | Task / Deliverable | Requirement / Black Book Mapping | Owner | Planned Hours | Illustrative Planned Date | Dependencies | Status | Completion Date | Milestone / Workstream Label | Issue / Limitation | Deliverable / Evidence | Source Notes | Actual Hours
AF-001 | 1 | Foundation | Finalize AdmitFlow product scope and positioning | Product definition | Zahir | 3 | 2026-09-25 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Foundation | No task-specific issue recorded. | docs/PROJECT_SPEC.md; docs/ADMITFLOW_BLACK_BOOK.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-002 | 1 | Foundation | Review BDS-03 requirements and acceptance gates | Faculty requirements | Samiksha | 3 | 2026-09-25 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Foundation | No task-specific issue recorded. | docs/ACCEPTANCE_CRITERIA.md; docs/PROJECT_SPEC.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-003 | 2 | Planning | Set up GitHub repo, issue board and workflow | Engineering evidence | Zahir | 3 | 2026-09-25 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Planning | No task-specific issue recorded. | .git; Git history (repository metadata) | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-004 | 2 | Planning | Create backlog and milestone plan | Problem brief | Samiksha | 4 | 2026-09-25 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Planning | No task-specific issue recorded. | docs/DEVELOPMENT_PLAN.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-005 | 3 | Requirements | Stakeholder map and personas | Chapter 1 / Problem validation | Samiksha | 4 | 2026-09-25 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Requirements | No task-specific issue recorded. | docs/PROJECT_SPEC.md; docs/ADMITFLOW_BLACK_BOOK.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-006 | 3 | Requirements | User stories and acceptance criteria | Chapter 2 / Requirements | Samiksha | 5 | 2026-09-25 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Requirements | No task-specific issue recorded. | docs/ACCEPTANCE_CRITERIA.md; docs/PROJECT_SPEC.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-007 | 3 | Requirements | Misuse cases, risks and scope exclusions | Threat/misuse analysis | Samiksha | 4 | 2026-09-25 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Requirements | No task-specific issue recorded. | docs/PROJECT_SPEC.md; docs/ADMITFLOW_BLACK_BOOK.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-008 | 4 | Data | Admission funnel/event data model | Funnel model / ERD | Zahir | 6 | 2026-09-25 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Data | No task-specific issue recorded. | docs/ARCHITECTURE.md; docs/DATA_DICTIONARY.md; backend/admitflow/analytics.py | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-009 | 4 | Data | Data dictionary and synthetic-data protocol if needed | Data/model package | Zahir | 5 | 2026-09-25 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Data | No task-specific issue recorded. | backend/admitflow/data_generator.py; scripts/generate_dataset.py; docs/DATA_DICTIONARY.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-010 | 4 | Data | Data intake/import | Integrated prototype | Zahir | 6 | 2026-09-26 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Data | Data intake/import is not evidenced; current application reads the supplied CSV. | Not located; planned deliverable. The application reads the supplied CSV; no data intake/import workflow is documented. | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-011 | 4 | Data | Data validation and quality checks | Data-quality monitoring | Zahir | 6 | 2026-09-26 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Data | No task-specific issue recorded. | evidence/dataset/validation_report.json; backend/admitflow/data_generator.py | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-012 | 5 | Analytics | Funnel conversion calculations | Funnel analysis | Zahir | 7 | 2026-09-26 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Analytics | No task-specific issue recorded. | evidence/metrics/analytics_report.json; backend/admitflow/analytics.py | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-013 | 5 | Analytics | Cohort analytics and filters | Cohort analysis | Zahir | 7 | 2026-09-26 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Analytics | No task-specific issue recorded. | evidence/metrics/analytics_report.json; backend/admitflow/analytics.py | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-014 | 5 | Analytics | Programme comparison | Programme comparison | Zahir | 5 | 2026-09-26 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Analytics | No task-specific issue recorded. | evidence/metrics/analytics_report.json; backend/admitflow/analytics.py | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-015 | 6 | ML | Target, prediction horizon and leakage rules | ML methodology | Zahir | 4 | 2026-09-26 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: ML | No task-specific issue recorded. | docs/MODEL_METHODOLOGY.md; backend/admitflow/forecast.py | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-016 | 6 | ML | Reproducible baseline model | Baseline comparison | Zahir | 7 | 2026-09-26 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: ML | No task-specific issue recorded. | evidence/models/model_report.json; evidence/models/admitflow_model.joblib; backend/admitflow/ml.py | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-017 | 6 | ML | Advanced model | Innovation layer | Zahir | 9 | 2026-09-26 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: ML | No task-specific issue recorded. | evidence/models/model_report.json; evidence/models/admitflow_model.joblib; backend/admitflow/ml.py | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-018 | 6 | ML | Log loss and calibration evaluation | Evaluation dossier | Zahir | 6 | 2026-09-27 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: ML | Model metrics are weak; random forest predicts no positive cases at threshold 0.5. | evidence/models/model_report.json; docs/MODEL_METHODOLOGY.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-019 | 6 | ML | Forecast deviation and segment stability | Evaluation dossier | Zahir | 5 | 2026-09-27 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: ML | Forecast uses six annual observations and is illustrative, not operationally validated. | evidence/metrics/forecast_report.json; docs/MODEL_METHODOLOGY.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-020 | 6 | ML | Explainability and error analysis | Model/system card | Zahir | 6 | 2026-09-27 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: ML | Classifier results are not decision-ready. | evidence/models/model_report.json; docs/MODEL_METHODOLOGY.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-021 | 7 | Backend | API/data contracts | Solution design | Zahir | 5 | 2026-09-27 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Backend | No task-specific issue recorded. | docs/API.md; backend/admitflow/server.py | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-022 | 7 | Backend | Authentication and authorization | Security | Zahir | 6 | 2026-09-27 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Backend | No task-specific issue recorded. | docs/API.md; backend/admitflow/auth.py; evidence/security/auth_check.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-023 | 7 | Backend | Forecast inference API | Deployable inference | Zahir | 6 | 2026-09-27 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Backend | No task-specific issue recorded. | docs/API.md; backend/admitflow/forecast.py; evidence/api/api_smoke.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-024 | 7 | Backend | Scenario simulation service | Scenario simulation | Zahir | 7 | 2026-09-27 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Backend | No task-specific issue recorded. | backend/admitflow/scenario.py; evidence/metrics/scenario_report.json; evidence/api/api_smoke.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-025 | 7 | Backend | Actions and audit APIs | Action dashboard / audit | Zahir | 5 | 2026-09-27 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Backend | No task-specific issue recorded. | docs/API.md; backend/admitflow/server.py; evidence/api/api_smoke.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-026 | 8 | Frontend | Premium application shell | UI design | Zahir | 5 | 2026-09-27 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/App.jsx; evidence/screenshots/login-redesign.png; evidence/screenshots/dashboard-redesign.png | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-027 | 8 | Frontend | Command Center dashboard | Action dashboard | Zahir | 8 | 2026-09-28 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/App.jsx; evidence/screenshots/dashboard-redesign.png; evidence/screenshots/dashboard-dark.png | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-028 | 8 | Frontend | Funnel Explorer | Conversion visualization | Zahir | 6 | 2026-09-28 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/pages/WorkspacePages.jsx; evidence/metrics/analytics_report.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-029 | 8 | Frontend | Cohort Explorer | Cohort analysis | Zahir | 6 | 2026-09-28 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/pages/WorkspacePages.jsx; evidence/metrics/analytics_report.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-030 | 8 | Frontend | Forecasting workspace | Yield prediction | Zahir | 6 | 2026-09-28 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/pages/WorkspacePages.jsx; evidence/metrics/forecast_report.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-031 | 8 | Frontend | Scenario Lab | Scenario simulation | Zahir | 8 | 2026-09-28 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/pages/WorkspacePages.jsx; evidence/metrics/scenario_report.json; evidence/screenshots/scenario-redesign.png | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-032 | 8 | Frontend | Programme Comparison | Programme comparison | Zahir | 5 | 2026-09-28 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/pages/WorkspacePages.jsx; evidence/metrics/analytics_report.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-033 | 8 | Frontend | Data Quality center | Data-quality monitoring | Zahir | 5 | 2026-09-28 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/pages/WorkspacePages.jsx; evidence/dataset/validation_report.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-034 | 8 | Frontend | Actions and Audit screens | Action + audit | Zahir | 5 | 2026-09-28 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/pages/WorkspacePages.jsx; backend/admitflow/server.py | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-035 | 8 | Frontend | Model/System transparency panel | Model/system card | Zahir | 4 | 2026-09-29 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/pages/WorkspacePages.jsx; evidence/models/model_report.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-036 | 8 | Frontend | Assistant | Mandatory deliverables | Zahir | 6 | 2026-09-29 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Frontend | No task-specific issue recorded. | frontend/src/components/AssistantPanel.jsx; docs/API.md; evidence/screenshots/assistant-offline.png | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-037 | 9 | Engineering | Unit tests | Testing | Zahir | 6 | 2026-09-29 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Engineering | No task-specific issue recorded. | tests/; evidence/tests/backend_pytest.txt; frontend/src/App.test.jsx; evidence/tests/frontend_vitest.txt | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-038 | 9 | Engineering | Integration/API tests | Testing | Zahir | 6 | 2026-09-29 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Engineering | No task-specific issue recorded. | tests/test_api.py; tests/test_security.py; evidence/api/api_smoke.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-039 | 9 | Engineering | Failure-mode and robustness tests | Acceptance gates | Zahir | 5 | 2026-09-29 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Engineering | No task-specific issue recorded. | tests/; docs/TESTING.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-040 | 9 | Engineering | Security/privacy checks | Security/privacy | Zahir | 5 | 2026-09-29 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Engineering | No task-specific issue recorded. | tests/test_auth.py; tests/test_security.py; evidence/security/auth_check.json | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-041 | 9 | Engineering | Docker/reproducible deployment | Deployment | Zahir | 4 | 2026-09-29 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Engineering | Not evidenced in project files; do not mark complete without container artifacts. | Not located; planned deliverable (no Docker configuration or container deployment evidence identified). | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-042 | 9 | Engineering | CI/CD pipeline | Engineering evidence | Zahir | 4 | 2026-09-29 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Engineering | Not evidenced in project files; do not mark complete without CI/CD artifacts. | Not located; planned deliverable (no CI/CD workflow evidence identified). | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-043 | 9 | Engineering | Logs, health and monitoring | Observability | Zahir | 5 | 2026-09-30 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Engineering | No task-specific issue recorded. | docs/API.md; backend/admitflow/server.py (local health route only) | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-044 | 10 | Deployment | Live deployment | Deployable demo | Zahir | 6 | 2026-09-30 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Deployment | Live deployment is not evidenced; project is documented as a local prototype. | Not located; planned deliverable (project documentation describes a local prototype, not live deployment). | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-045 | 10 | Deployment | Production smoke tests | Deployment evidence | Zahir | 3 | 2026-09-30 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Deployment | Available smoke evidence is local API verification, not production deployment testing. | evidence/api/api_smoke.json (local API smoke evidence; production deployment not verified). | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-046 | 11 | Documentation | C4 architecture and data-flow diagrams | Chapter 3 | Samiksha | 5 | 2026-09-30 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Documentation | No task-specific issue recorded. | docs/ARCHITECTURE.md; docs/ADMITFLOW_BLACK_BOOK.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-047 | 11 | Documentation | ER diagram | Chapter 3 | Samiksha | 4 | 2026-09-30 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Documentation | No task-specific issue recorded. | docs/ADMITFLOW_BLACK_BOOK.md (database ER diagram) | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-048 | 11 | Documentation | DFD Level 0/1 | Chapter 3 | Samiksha | 5 | 2026-09-30 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Documentation | No task-specific issue recorded. | docs/ARCHITECTURE.md; docs/ADMITFLOW_BLACK_BOOK.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-049 | 11 | Documentation | UML use-case/class/sequence/state | Chapter 3 | Samiksha | 7 | 2026-09-30 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Documentation | No task-specific issue recorded. | docs/ARCHITECTURE.md; docs/ADMITFLOW_BLACK_BOOK.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-050 | 11 | Documentation | Gantt chart | Chapter 3 | Samiksha | 3 | 2026-09-30 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Documentation | Dated Gantt cannot be substantiated; task start/finish dates are absent. | docs/ADMITFLOW_BLACK_BOOK.md (schedule note; dated Gantt is unsupported because task dates are absent). | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-051 | 11 | Documentation | Test-case documentation | Chapter 4 | Samiksha | 7 | 2026-09-30 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Documentation | No task-specific issue recorded. | docs/TESTING.md; tests/; evidence/tests/ | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-052 | 11 | Documentation | Results/screenshots/evidence index | Chapter 5 | Samiksha | 5 | 2026-10-01 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Documentation | No task-specific issue recorded. | docs/EVIDENCE.md; evidence/reports/evidence_manifest.json; evidence/screenshots/ | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-053 | 11 | Documentation | Evaluation dossier structure | Chapter 5 | Samiksha | 5 | 2026-10-01 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Documentation | No task-specific issue recorded. | docs/MODEL_METHODOLOGY.md; docs/ADMITFLOW_VIVA_PREPARATION.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-054 | 11 | Documentation | Model/system card inputs | Chapter 5/7 | Samiksha | 4 | 2026-10-01 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Documentation | No task-specific issue recorded. | docs/MODEL_METHODOLOGY.md; docs/ADMITFLOW_VIVA_PREPARATION.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-055 | 11 | Documentation | Admin/user guide content | Mandatory deliverables | Samiksha | 5 | 2026-10-01 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Documentation | No dedicated admin/user guide was located. | Not located as a dedicated user guide; planned deliverable. | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-056 | 12 | Black Book | Chapter 1 ? Introduction | Black Book Ch. 1 | Samiksha | 6 | 2026-10-01 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Black Book | No task-specific issue recorded. | docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 1 | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-057 | 12 | Black Book | Chapter 2 ? System Analysis | Black Book Ch. 2 | Samiksha | 7 | 2026-10-01 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Black Book | No task-specific issue recorded. | docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 2 | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-058 | 12 | Black Book | Chapter 3 ? System Design | Black Book Ch. 3 | Samiksha | 8 | 2026-10-01 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Black Book | No task-specific issue recorded. | docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 3 | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-059 | 12 | Black Book | Chapter 4 ? Implementation & Testing | Black Book Ch. 4 | Samiksha | 8 | 2026-10-01 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Black Book | No task-specific issue recorded. | docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 4 | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-060 | 12 | Black Book | Chapter 5 ? Results & Discussions | Black Book Ch. 5 | Samiksha | 8 | 2026-10-02 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Black Book | No task-specific issue recorded. | docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 5 | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-061 | 12 | Black Book | Chapter 6 ? Conclusion & Future Work | Black Book Ch. 6 | Samiksha | 4 | 2026-10-02 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Black Book | No task-specific issue recorded. | docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 6 | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-062 | 12 | Black Book | Chapter 7 ? References | Black Book Ch. 7 | Samiksha | 3 | 2026-10-02 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Black Book | No task-specific issue recorded. | docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 7 | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-063 | 12 | Black Book | Front matter using faculty sample | Cover/certificate/abstract/etc. | Samiksha | 5 | 2026-10-02 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Black Book | College-specific front matter and faculty template remain pending. | docs/ADMITFLOW_BLACK_BOOK.md (front matter placeholders remain pending; faculty template not supplied). | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-064 | 13 | QA | Full regression and acceptance checklist | Final acceptance | Both | 6 | 2026-10-02 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: QA | No task-specific issue recorded. | evidence/tests/backend_pytest.txt; evidence/tests/frontend_vitest.txt; docs/ACCEPTANCE_CRITERIA.md | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-065 | 13 | QA | Stakeholder usability evaluation | Dashboard usability | Both | 5 | 2026-10-02 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: QA | No stakeholder usability evaluation evidence was located. | Not located; planned deliverable (no stakeholder usability study evidence identified). | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-066 | 14 | Demo | 5?8 minute product demo | Mandatory demo | Both | 4 | 2026-10-02 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Demo | No recorded product-demo artifact was located. | Not located; planned deliverable (no recorded product-demo artifact identified). | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-067 | 14 | Demo | Presentation and viva evidence | Final presentation | Both | 5 | 2026-10-02 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Demo | No presentation artifact was located. | Not located; planned deliverable (no presentation evidence located). | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.
AF-068 | 15 | Final | Finalize actual contribution evidence and logs | Individual ownership | Both | 4 | 2026-10-03 | Not specified in supplied task-distribution image | Not recorded at task level | Not recorded | Planned workstream: Final | Individual task contributions and actual work logs are not recorded. | Not recorded; individual contribution logs and actual hours were not supplied. | Task ID, owner and planned hours transcribed from supplied distribution. Illustrative schedule date only; no actual work date was supplied.

## Timeline & Dependencies
Phase Order | Phase | Task IDs | Planned Hours | Task Count | Illustrative Planned Date | Dependencies | Timeline Basis / Notes | Status
1 | Foundation | AF-001, AF-002 |  |  | 2026-09-25 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
2 | Planning | AF-003, AF-004 |  |  | 2026-09-25 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
3 | Requirements | AF-005, AF-006, AF-007 |  |  | 2026-09-25 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
4 | Data | AF-008, AF-009, AF-010, AF-011 |  |  | 2026-09-25 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
5 | Analytics | AF-012, AF-013, AF-014 |  |  | 2026-09-26 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
6 | ML | AF-015, AF-016, AF-017, AF-018, AF-019, AF-020 |  |  | 2026-09-26 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
7 | Backend | AF-021, AF-022, AF-023, AF-024, AF-025 |  |  | 2026-09-27 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
8 | Frontend | AF-026, AF-027, AF-028, AF-029, AF-030, AF-031, AF-032, AF-033, AF-034, AF-035, AF-036 |  |  | 2026-09-27 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
9 | Engineering | AF-037, AF-038, AF-039, AF-040, AF-041, AF-042, AF-043 |  |  | 2026-09-29 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
10 | Deployment | AF-044, AF-045 |  |  | 2026-09-30 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
11 | Documentation | AF-046, AF-047, AF-048, AF-049, AF-050, AF-051, AF-052, AF-053, AF-054, AF-055 |  |  | 2026-09-30 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
12 | Black Book | AF-056, AF-057, AF-058, AF-059, AF-060, AF-061, AF-062, AF-063 |  |  | 2026-10-01 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
13 | QA | AF-064, AF-065 |  |  | 2026-10-02 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
14 | Demo | AF-066, AF-067 |  |  | 2026-10-02 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded
15 | Final | AF-068 |  |  | 2026-10-03 | Not specified in supplied plan | Illustrative phase ordering only; actual dependencies were not supplied. | Planned; task-level status not recorded

## Work Log
Date | Task ID | Owner / Actor | Activity | Actual Hours | Evidence | Outcome
2026-10-02 | CLOSEOUT | Automated local run (student task split not identified) | Final local verification and evidence capture |  | docs/FINAL_VERIFICATION.md | Automated checks pass; model limitations recorded.

## Evidence Register
Evidence ID | Date | Task ID(s) | Evidence Type | Description | File Path | Result | Verified By / Source | Notes
AF-E01 | 2026-10-02 | AF-011 | Execution artifact | Dataset validation | evidence/dataset/validation_report.json | PASS | Automated local run | 4,200 rows; no validation issues.
AF-E02 | 2026-10-02 | AF-012; AF-013; AF-014 | Execution artifact | Analytics report | evidence/metrics/analytics_report.json | PASS | Automated local run | Funnel, cohorts, programme and attribution outputs.
AF-E03 | 2026-10-02 | AF-016; AF-017; AF-018; AF-020 | Execution artifact | Model report and artifact | evidence/models/model_report.json; evidence/models/admitflow_model.joblib | GENERATED WITH LIMITATIONS | Automated local run | Random forest predicts no positives at threshold 0.5; not decision-ready.
AF-E04 | 2026-10-02 | AF-015; AF-019; AF-023 | Execution artifact | Forecast report | evidence/metrics/forecast_report.json | PASS WITH LIMITATIONS | Automated local run | Two-year holdout over six annual observations.
AF-E05 | 2026-10-02 | AF-024; AF-031 | Execution artifact | Scenario report | evidence/metrics/scenario_report.json | PASS | Automated local run | Deterministic scenario output.
AF-E06 | 2026-10-02 | AF-021; AF-022; AF-023; AF-024; AF-025; AF-038 | Execution artifact | API smoke report | evidence/api/api_smoke.json | PASS | Automated local run | 10 protected API operations returned successfully.
AF-E07 | 2026-10-02 | AF-022; AF-040 | Execution artifact | Auth boundary report | evidence/security/auth_check.json | PASS | Automated local run | 401 without token; secrets omitted.
AF-E08 | 2026-10-02 | AF-026; AF-027 | Screenshot | Desktop dashboard | evidence/screenshots/dashboard.png | CAPTURED | Automated local run | Authenticated local dashboard.
AF-E09 | 2026-10-02 | AF-026; AF-028; AF-029; AF-030; AF-032 | Screenshot | Mobile dashboard | evidence/screenshots/dashboard-mobile.png | CAPTURED | Automated local run | 390px dashboard; not per-page evidence.
AF-E10 | 2026-10-02 | AF-037; AF-038; AF-039; AF-040; AF-064 | Test output | Backend tests | evidence/tests/backend_pytest.txt | PASS | Automated local run | 20 passed.
AF-E11 | 2026-10-02 | AF-036; AF-037; AF-064 | Test output | Frontend tests | evidence/tests/frontend_vitest.txt | PASS | Automated local run | 3 passed.
AF-E12 | 2026-10-02 | AF-037; AF-042 | Test output | Frontend lint | evidence/tests/frontend_lint.txt | PASS | Automated local run | Final verification records lint as clean; not CI/CD evidence.
AF-E13 | 2026-10-02 | AF-045 | Build output | Frontend build | evidence/tests/frontend_build.txt | PASS WITH WARNING | Automated local run | Build succeeds with bundle-size warning; not a production deployment test.
AF-E14 | 2026-10-02 | AF-046; AF-047; AF-048; AF-049; AF-051; AF-052; AF-053; AF-054; AF-056; AF-057; AF-058; AF-059; AF-060; AF-061; AF-062; AF-063 | Report | Project documentation | docs/FINAL_VERIFICATION.md; docs/FINAL_PROJECT_REPORT.md; docs/ADMITFLOW_BLACK_BOOK.md | PASS | Project documentation | College-specific fields remain pending.
AF-E15 | 2026-10-02 | AF-031 | Screenshot | Scenario UI | evidence/screenshots/scenario.png | CAPTURED | Automated local run | Scenario at twice baseline application volume.
AF-E16 | Not recorded | AF-026; AF-027; AF-030; AF-031 | Screenshot set | Redesigned UI captures | evidence/screenshots/dashboard-redesign.png; evidence/screenshots/dashboard-dark.png; evidence/screenshots/dashboard-mobile-redesign.png; evidence/screenshots/scenario-redesign.png; evidence/screenshots/login-redesign.png; evidence/screenshots/assistant-offline.png | CAPTURED | Evidence artifacts | Individual capture date not in manifest.

## Test Register
Test ID | Task ID(s) | Test | Command | Expected | Actual | Status | Evidence
AF-T01 | AF-037; AF-039; AF-040; AF-064 | Backend pytest suite | python -m pytest -q | All tests pass | 20 passed; 0 failed | PASS | evidence/tests/backend_pytest.txt
AF-T02 | AF-036; AF-037; AF-064 | Frontend Vitest suite | npm test | All tests pass | 3 passed | PASS | evidence/tests/frontend_vitest.txt
AF-T03 | AF-037; AF-042 | Frontend lint | npm run lint | No diagnostics | Clean per final verification | PASS | evidence/tests/frontend_lint.txt
AF-T04 | AF-045 | Frontend production build | npm run build | Build succeeds | Build succeeded; bundle-size warning present | PASS WITH WARNING | evidence/tests/frontend_build.txt
AF-T05 | AF-021; AF-022; AF-023; AF-024; AF-025; AF-038 | Authenticated API smoke checks | python scripts/capture_evidence.py | Protected routes respond successfully | 10 protected route operations successful | PASS | evidence/api/api_smoke.json

## Model Results
Plan Task IDs | Model | Dataset | Target | ROC-AUC | PR-AUC | Accuracy | Precision | Recall | F1 | Run Date | Artifact | Status / Interpretation
AF-016; AF-018; AF-020 | Logistic Regression | data/admission_data.csv (synthetic) | enrolled | 0.5573 | 0.0964 | 0.6143 | 0.1028 | 0.4659 | 0.1684 | 2026-10-02 | evidence/models/model_report.json; evidence/models/admitflow_model.joblib | Evaluated; weak discrimination; not decision-ready.
AF-017; AF-018; AF-020 | Random Forest | data/admission_data.csv (synthetic) | enrolled | 0.5195 | 0.1037 | 0.9162 | 0 | 0 | 0 | 2026-10-02 | evidence/models/model_report.json; evidence/models/admitflow_model.joblib | Evaluated; predicts no positive cases at threshold 0.5; not decision-ready.

## Submission Checklist
Submission Item | Current Value / State | Basis / Action Needed
Project title | Admission Conversion Forecasting with Funnel Attribution and Scenario Simulation | docs/ADMITFLOW_BLACK_BOOK.md
Project name | AdmitFlow v2 | docs/PROJECT_SPEC.md
Students | Samiksha; Zahir | Named in black book; no per-task contribution split recorded.
Programme / course | T.Y. B.Sc. Data Science; BDS-03 Capstone Project | Confirm exact college-required wording.
Academic year | 2026-27 | docs/ADMITFLOW_BLACK_BOOK.md
College | KES' Shroff College | Confirm official legal/institute name and cover-page format.
Project guide | Not provided | Obtain guide name and required approval/signature.
PRN / roll numbers / division / semester | Not provided or confirmed | Complete from official student records.
Schedule dates | Illustrative planned dates: 25-Sep-2026 to 03-Oct-2026 | Synthetic planning placeholders only; replace with actual dates if this is intended as a historical work record.
Task completion dates | Not recorded | Source tracker has no task completion dates.
Actual hours | To be entered by students | Actual-hours cells are intentionally blank in Master Tracker and Work Log.
Student signatures / declaration | Pending student review and signatures | Black book marks declaration and signatures pending.
Official logo / approved cover layout | Not provided | Insert only the college-approved asset/template.
Status interpretation | Legacy A1-A17 tracker marked Completed; AF-001-AF-068 task-level status not recorded. | Do not infer granular completion from the coarse legacy tracker; verify each planned row before claiming completion.
Known project limitations | Synthetic data; weak classifiers; short forecast history; process-local audit log; build-size warning | See docs/FINAL_VERIFICATION.md and docs/ADMITFLOW_BLACK_BOOK.md.

## Legacy Crosswalk
Legacy Task ID | Legacy Task | Planned Distribution Task IDs | Crosswalk Note
A1 | Create project specification | AF-001; AF-005; AF-006; AF-007 | Scope and requirements.
A2 | Create architecture blueprint | AF-008; AF-021; AF-046; AF-047; AF-048; AF-049 | Architecture/API/design documentation.
A3 | Create development plan | AF-003; AF-004 | Repository workflow and backlog.
A4 | Create acceptance criteria | AF-002; AF-006; AF-064 | Acceptance and regression criteria.
A5 | Initialize evidence structure | AF-051; AF-052 | Testing and evidence indexing.
A6 | Create Git repository | AF-003 | Repository and workflow.
A7 | Generate synthetic dataset | AF-008; AF-009; AF-010; AF-011 | Data model, dictionary, intake plan, validation.
A8 | Build funnel analytics | AF-012 | Funnel calculations.
A9 | Build cohort analytics | AF-013; AF-014 | Cohorts and programme comparison.
A10 | Implement attribution | No direct granular attribution task in supplied distribution | Attribution remains in existing analytics evidence; no exact planned row is identified.
A11 | Train baseline and advanced models | AF-015; AF-016; AF-017; AF-018; AF-020 | Model planning, training and evaluation.
A12 | Build forecast pipeline | AF-015; AF-019; AF-023; AF-030 | Forecast method, API and UI.
A13 | Build scenario engine | AF-024; AF-031 | Scenario service and interface.
A14 | Implement FastAPI backend | AF-021; AF-022; AF-023; AF-024; AF-025 | API and backend services.
A15 | Build analytics frontend | AF-026; AF-027; AF-028; AF-029; AF-030; AF-031; AF-032; AF-033; AF-034; AF-035; AF-036 | Frontend shell and workspaces.
A16 | Run full verification suite | AF-037; AF-038; AF-039; AF-040; AF-064 | Automated verification.
A17 | Prepare final project report | AF-046; AF-047; AF-048; AF-049; AF-050; AF-051; AF-052; AF-053; AF-054; AF-055; AF-056; AF-057; AF-058; AF-059; AF-060; AF-061; AF-062; AF-063; AF-067 | Documentation and submission.

## Samiksha Work Log
Illustrative Planned Date | Task ID | Planned Task / Activity | Assignment Basis | Planned Hours | Actual Hours | Actual Work Performed | Evidence (confirm contribution) | Outcome / Completion Notes | Entry Status
2026-09-25 | AF-002 | Review BDS-03 requirements and acceptance gates | Assigned to Samiksha in supplied plan | 3 |  |  | Potential project reference; verify this supports individual contribution: docs/ACCEPTANCE_CRITERIA.md; docs/PROJECT_SPEC.md |  | PLANNED ONLY - confirm actual work
2026-09-25 | AF-004 | Create backlog and milestone plan | Assigned to Samiksha in supplied plan | 4 |  |  | Potential project reference; verify this supports individual contribution: docs/DEVELOPMENT_PLAN.md |  | PLANNED ONLY - confirm actual work
2026-09-25 | AF-005 | Stakeholder map and personas | Assigned to Samiksha in supplied plan | 4 |  |  | Potential project reference; verify this supports individual contribution: docs/PROJECT_SPEC.md; docs/ADMITFLOW_BLACK_BOOK.md |  | PLANNED ONLY - confirm actual work
2026-09-25 | AF-006 | User stories and acceptance criteria | Assigned to Samiksha in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: docs/ACCEPTANCE_CRITERIA.md; docs/PROJECT_SPEC.md |  | PLANNED ONLY - confirm actual work
2026-09-25 | AF-007 | Misuse cases, risks and scope exclusions | Assigned to Samiksha in supplied plan | 4 |  |  | Potential project reference; verify this supports individual contribution: docs/PROJECT_SPEC.md; docs/ADMITFLOW_BLACK_BOOK.md |  | PLANNED ONLY - confirm actual work
2026-09-30 | AF-046 | C4 architecture and data-flow diagrams | Assigned to Samiksha in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: docs/ARCHITECTURE.md; docs/ADMITFLOW_BLACK_BOOK.md |  | PLANNED ONLY - confirm actual work
2026-09-30 | AF-047 | ER diagram | Assigned to Samiksha in supplied plan | 4 |  |  | Potential project reference; verify this supports individual contribution: docs/ADMITFLOW_BLACK_BOOK.md (database ER diagram) |  | PLANNED ONLY - confirm actual work
2026-09-30 | AF-048 | DFD Level 0/1 | Assigned to Samiksha in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: docs/ARCHITECTURE.md; docs/ADMITFLOW_BLACK_BOOK.md |  | PLANNED ONLY - confirm actual work
2026-09-30 | AF-049 | UML use-case/class/sequence/state | Assigned to Samiksha in supplied plan | 7 |  |  | Potential project reference; verify this supports individual contribution: docs/ARCHITECTURE.md; docs/ADMITFLOW_BLACK_BOOK.md |  | PLANNED ONLY - confirm actual work
2026-09-30 | AF-050 | Gantt chart | Assigned to Samiksha in supplied plan | 3 |  |  | Potential project reference; verify this supports individual contribution: docs/ADMITFLOW_BLACK_BOOK.md (schedule note; dated Gantt is unsupported because task dates are absent). |  | PLANNED ONLY - confirm actual work
2026-09-30 | AF-051 | Test-case documentation | Assigned to Samiksha in supplied plan | 7 |  |  | Potential project reference; verify this supports individual contribution: docs/TESTING.md; tests/; evidence/tests/ |  | PLANNED ONLY - confirm actual work
2026-10-01 | AF-052 | Results/screenshots/evidence index | Assigned to Samiksha in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: docs/EVIDENCE.md; evidence/reports/evidence_manifest.json; evidence/screenshots/ |  | PLANNED ONLY - confirm actual work
2026-10-01 | AF-053 | Evaluation dossier structure | Assigned to Samiksha in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: docs/MODEL_METHODOLOGY.md; docs/ADMITFLOW_VIVA_PREPARATION.md |  | PLANNED ONLY - confirm actual work
2026-10-01 | AF-054 | Model/system card inputs | Assigned to Samiksha in supplied plan | 4 |  |  | Potential project reference; verify this supports individual contribution: docs/MODEL_METHODOLOGY.md; docs/ADMITFLOW_VIVA_PREPARATION.md |  | PLANNED ONLY - confirm actual work
2026-10-01 | AF-055 | Admin/user guide content | Assigned to Samiksha in supplied plan | 5 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-10-01 | AF-056 | Chapter 1 ? Introduction | Assigned to Samiksha in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 1 |  | PLANNED ONLY - confirm actual work
2026-10-01 | AF-057 | Chapter 2 ? System Analysis | Assigned to Samiksha in supplied plan | 7 |  |  | Potential project reference; verify this supports individual contribution: docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 2 |  | PLANNED ONLY - confirm actual work
2026-10-01 | AF-058 | Chapter 3 ? System Design | Assigned to Samiksha in supplied plan | 8 |  |  | Potential project reference; verify this supports individual contribution: docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 3 |  | PLANNED ONLY - confirm actual work
2026-10-01 | AF-059 | Chapter 4 ? Implementation & Testing | Assigned to Samiksha in supplied plan | 8 |  |  | Potential project reference; verify this supports individual contribution: docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 4 |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-060 | Chapter 5 ? Results & Discussions | Assigned to Samiksha in supplied plan | 8 |  |  | Potential project reference; verify this supports individual contribution: docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 5 |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-061 | Chapter 6 ? Conclusion & Future Work | Assigned to Samiksha in supplied plan | 4 |  |  | Potential project reference; verify this supports individual contribution: docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 6 |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-062 | Chapter 7 ? References | Assigned to Samiksha in supplied plan | 3 |  |  | Potential project reference; verify this supports individual contribution: docs/ADMITFLOW_BLACK_BOOK.md ? Chapter 7 |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-063 | Front matter using faculty sample | Assigned to Samiksha in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: docs/ADMITFLOW_BLACK_BOOK.md (front matter placeholders remain pending; faculty template not supplied). |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-064 | Full regression and acceptance checklist | Joint assignment (verify each student's contribution) | 6 |  |  | Potential project reference; verify this supports individual contribution: evidence/tests/backend_pytest.txt; evidence/tests/frontend_vitest.txt; docs/ACCEPTANCE_CRITERIA.md |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-065 | Stakeholder usability evaluation | Joint assignment (verify each student's contribution) | 5 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-066 | 5?8 minute product demo | Joint assignment (verify each student's contribution) | 4 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-067 | Presentation and viva evidence | Joint assignment (verify each student's contribution) | 5 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-10-03 | AF-068 | Finalize actual contribution evidence and logs | Joint assignment (verify each student's contribution) | 4 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work

## Zahir Work Log
Illustrative Planned Date | Task ID | Planned Task / Activity | Assignment Basis | Planned Hours | Actual Hours | Actual Work Performed | Evidence (confirm contribution) | Outcome / Completion Notes | Entry Status
2026-09-25 | AF-001 | Finalize AdmitFlow product scope and positioning | Assigned to Zahir in supplied plan | 3 |  |  | Potential project reference; verify this supports individual contribution: docs/PROJECT_SPEC.md; docs/ADMITFLOW_BLACK_BOOK.md |  | PLANNED ONLY - confirm actual work
2026-09-25 | AF-003 | Set up GitHub repo, issue board and workflow | Assigned to Zahir in supplied plan | 3 |  |  | Potential project reference; verify this supports individual contribution: .git; Git history (repository metadata) |  | PLANNED ONLY - confirm actual work
2026-09-25 | AF-008 | Admission funnel/event data model | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: docs/ARCHITECTURE.md; docs/DATA_DICTIONARY.md; backend/admitflow/analytics.py |  | PLANNED ONLY - confirm actual work
2026-09-25 | AF-009 | Data dictionary and synthetic-data protocol if needed | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: backend/admitflow/data_generator.py; scripts/generate_dataset.py; docs/DATA_DICTIONARY.md |  | PLANNED ONLY - confirm actual work
2026-09-26 | AF-010 | Data intake/import | Assigned to Zahir in supplied plan | 6 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-09-26 | AF-011 | Data validation and quality checks | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: evidence/dataset/validation_report.json; backend/admitflow/data_generator.py |  | PLANNED ONLY - confirm actual work
2026-09-26 | AF-012 | Funnel conversion calculations | Assigned to Zahir in supplied plan | 7 |  |  | Potential project reference; verify this supports individual contribution: evidence/metrics/analytics_report.json; backend/admitflow/analytics.py |  | PLANNED ONLY - confirm actual work
2026-09-26 | AF-013 | Cohort analytics and filters | Assigned to Zahir in supplied plan | 7 |  |  | Potential project reference; verify this supports individual contribution: evidence/metrics/analytics_report.json; backend/admitflow/analytics.py |  | PLANNED ONLY - confirm actual work
2026-09-26 | AF-014 | Programme comparison | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: evidence/metrics/analytics_report.json; backend/admitflow/analytics.py |  | PLANNED ONLY - confirm actual work
2026-09-26 | AF-015 | Target, prediction horizon and leakage rules | Assigned to Zahir in supplied plan | 4 |  |  | Potential project reference; verify this supports individual contribution: docs/MODEL_METHODOLOGY.md; backend/admitflow/forecast.py |  | PLANNED ONLY - confirm actual work
2026-09-26 | AF-016 | Reproducible baseline model | Assigned to Zahir in supplied plan | 7 |  |  | Potential project reference; verify this supports individual contribution: evidence/models/model_report.json; evidence/models/admitflow_model.joblib; backend/admitflow/ml.py |  | PLANNED ONLY - confirm actual work
2026-09-26 | AF-017 | Advanced model | Assigned to Zahir in supplied plan | 9 |  |  | Potential project reference; verify this supports individual contribution: evidence/models/model_report.json; evidence/models/admitflow_model.joblib; backend/admitflow/ml.py |  | PLANNED ONLY - confirm actual work
2026-09-27 | AF-018 | Log loss and calibration evaluation | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: evidence/models/model_report.json; docs/MODEL_METHODOLOGY.md |  | PLANNED ONLY - confirm actual work
2026-09-27 | AF-019 | Forecast deviation and segment stability | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: evidence/metrics/forecast_report.json; docs/MODEL_METHODOLOGY.md |  | PLANNED ONLY - confirm actual work
2026-09-27 | AF-020 | Explainability and error analysis | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: evidence/models/model_report.json; docs/MODEL_METHODOLOGY.md |  | PLANNED ONLY - confirm actual work
2026-09-27 | AF-021 | API/data contracts | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: docs/API.md; backend/admitflow/server.py |  | PLANNED ONLY - confirm actual work
2026-09-27 | AF-022 | Authentication and authorization | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: docs/API.md; backend/admitflow/auth.py; evidence/security/auth_check.json |  | PLANNED ONLY - confirm actual work
2026-09-27 | AF-023 | Forecast inference API | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: docs/API.md; backend/admitflow/forecast.py; evidence/api/api_smoke.json |  | PLANNED ONLY - confirm actual work
2026-09-27 | AF-024 | Scenario simulation service | Assigned to Zahir in supplied plan | 7 |  |  | Potential project reference; verify this supports individual contribution: backend/admitflow/scenario.py; evidence/metrics/scenario_report.json; evidence/api/api_smoke.json |  | PLANNED ONLY - confirm actual work
2026-09-27 | AF-025 | Actions and audit APIs | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: docs/API.md; backend/admitflow/server.py; evidence/api/api_smoke.json |  | PLANNED ONLY - confirm actual work
2026-09-27 | AF-026 | Premium application shell | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/App.jsx; evidence/screenshots/login-redesign.png; evidence/screenshots/dashboard-redesign.png |  | PLANNED ONLY - confirm actual work
2026-09-28 | AF-027 | Command Center dashboard | Assigned to Zahir in supplied plan | 8 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/App.jsx; evidence/screenshots/dashboard-redesign.png; evidence/screenshots/dashboard-dark.png |  | PLANNED ONLY - confirm actual work
2026-09-28 | AF-028 | Funnel Explorer | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/pages/WorkspacePages.jsx; evidence/metrics/analytics_report.json |  | PLANNED ONLY - confirm actual work
2026-09-28 | AF-029 | Cohort Explorer | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/pages/WorkspacePages.jsx; evidence/metrics/analytics_report.json |  | PLANNED ONLY - confirm actual work
2026-09-28 | AF-030 | Forecasting workspace | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/pages/WorkspacePages.jsx; evidence/metrics/forecast_report.json |  | PLANNED ONLY - confirm actual work
2026-09-28 | AF-031 | Scenario Lab | Assigned to Zahir in supplied plan | 8 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/pages/WorkspacePages.jsx; evidence/metrics/scenario_report.json; evidence/screenshots/scenario-redesign.png |  | PLANNED ONLY - confirm actual work
2026-09-28 | AF-032 | Programme Comparison | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/pages/WorkspacePages.jsx; evidence/metrics/analytics_report.json |  | PLANNED ONLY - confirm actual work
2026-09-28 | AF-033 | Data Quality center | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/pages/WorkspacePages.jsx; evidence/dataset/validation_report.json |  | PLANNED ONLY - confirm actual work
2026-09-28 | AF-034 | Actions and Audit screens | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/pages/WorkspacePages.jsx; backend/admitflow/server.py |  | PLANNED ONLY - confirm actual work
2026-09-29 | AF-035 | Model/System transparency panel | Assigned to Zahir in supplied plan | 4 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/pages/WorkspacePages.jsx; evidence/models/model_report.json |  | PLANNED ONLY - confirm actual work
2026-09-29 | AF-036 | Assistant | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: frontend/src/components/AssistantPanel.jsx; docs/API.md; evidence/screenshots/assistant-offline.png |  | PLANNED ONLY - confirm actual work
2026-09-29 | AF-037 | Unit tests | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: tests/; evidence/tests/backend_pytest.txt; frontend/src/App.test.jsx; evidence/tests/frontend_vitest.txt |  | PLANNED ONLY - confirm actual work
2026-09-29 | AF-038 | Integration/API tests | Assigned to Zahir in supplied plan | 6 |  |  | Potential project reference; verify this supports individual contribution: tests/test_api.py; tests/test_security.py; evidence/api/api_smoke.json |  | PLANNED ONLY - confirm actual work
2026-09-29 | AF-039 | Failure-mode and robustness tests | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: tests/; docs/TESTING.md |  | PLANNED ONLY - confirm actual work
2026-09-29 | AF-040 | Security/privacy checks | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: tests/test_auth.py; tests/test_security.py; evidence/security/auth_check.json |  | PLANNED ONLY - confirm actual work
2026-09-29 | AF-041 | Docker/reproducible deployment | Assigned to Zahir in supplied plan | 4 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-09-29 | AF-042 | CI/CD pipeline | Assigned to Zahir in supplied plan | 4 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-09-30 | AF-043 | Logs, health and monitoring | Assigned to Zahir in supplied plan | 5 |  |  | Potential project reference; verify this supports individual contribution: docs/API.md; backend/admitflow/server.py (local health route only) |  | PLANNED ONLY - confirm actual work
2026-09-30 | AF-044 | Live deployment | Assigned to Zahir in supplied plan | 6 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-09-30 | AF-045 | Production smoke tests | Assigned to Zahir in supplied plan | 3 |  |  | Potential project reference; verify this supports individual contribution: evidence/api/api_smoke.json (local API smoke evidence; production deployment not verified). |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-064 | Full regression and acceptance checklist | Joint assignment (verify each student's contribution) | 6 |  |  | Potential project reference; verify this supports individual contribution: evidence/tests/backend_pytest.txt; evidence/tests/frontend_vitest.txt; docs/ACCEPTANCE_CRITERIA.md |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-065 | Stakeholder usability evaluation | Joint assignment (verify each student's contribution) | 5 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-066 | 5?8 minute product demo | Joint assignment (verify each student's contribution) | 4 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-10-02 | AF-067 | Presentation and viva evidence | Joint assignment (verify each student's contribution) | 5 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work
2026-10-03 | AF-068 | Finalize actual contribution evidence and logs | Joint assignment (verify each student's contribution) | 4 |  |  | To be completed only if work is performed and an artifact is created. |  | PLANNED ONLY - confirm actual work