## Master Checklist
Task ID | Phase | Task | Requirement | Planned Hours | Owner | Status | Completed Date | Actual Hours | Evidence | Notes
A1 | Foundation | Create project specification | Project docs and scope | 4 | Project Agent | Completed |  |  | docs/PROJECT_SPEC.md | Initial project scope defined.
A2 | Foundation | Create architecture blueprint | System design and stack | 4 | Project Agent | Completed |  |  | docs/ARCHITECTURE.md | Core architecture documented.
A3 | Foundation | Create development plan | Execution plan | 3 | Project Agent | Completed |  |  | docs/DEVELOPMENT_PLAN.md | Milestones defined.
A4 | Foundation | Create acceptance criteria | Evidence-based completion gates | 3 | Project Agent | Completed |  |  | docs/ACCEPTANCE_CRITERIA.md | Verification criteria established.
A5 | Foundation | Initialize evidence structure | Evidence registry | 2 | Project Agent | Completed |  |  | evidence/README.md | Evidence policy documented.
A6 | Foundation | Create Git repository | Source control | 1 | Project Agent | In Progress |  |  |  | Git repository will be initialized during setup.
A7 | Dataset | Generate synthetic dataset | Dataset generation and validation | 12 | Data Science Agent | Not Started |  |  |  | Dataset work begins after foundation verification.
A8 | Analytics | Build funnel analytics | Funnel metrics and conversion analysis | 8 | Data Science Agent | Not Started |  |  |  | Requires generated dataset.
A9 | Analytics | Build cohort analytics | Cohort and segment analysis | 8 | Data Science Agent | Not Started |  |  |  | Requires validated dataset.
A10 | Analytics | Implement attribution | Descriptive attribution analysis | 6 | Data Science Agent | Not Started |  |  |  | Must avoid causal claims.
A11 | ML | Train baseline and advanced models | Model training and comparison | 12 | ML Agent | Not Started |  |  |  | Model metrics to be captured from execution.
A12 | Forecasting | Build forecast pipeline | H1/H2/H4/H6 forecast evaluation | 10 | Data Science Agent | Not Started |  |  |  | Temporal leakage checks required.
A13 | Simulation | Build scenario engine | Deterministic scenario lab | 8 | Analytics Agent | Not Started |  |  |  | Scenario outputs must be deterministic.
A14 | Backend | Implement FastAPI backend | API and backend services | 12 | Backend Agent | Not Started |  |  |  | Includes auth and audit flows.
A15 | Frontend | Build analytics frontend | UI, dashboard, and charts | 14 | Frontend Agent | Not Started |  |  |  | Must include light/dark theme.
A16 | Testing | Run full verification suite | Unit, integration, failures, security, and UI | 10 | QA Agent | Not Started |  |  |  | Evidence required before final verification.
A17 | Documentation | Prepare final project report | Final project summary and verification | 4 | Project Agent | Not Started |  |  |  | Final evidence must be linked.

## Work Log
Date | Task ID | Owner | Activity | Actual Hours | Evidence | Outcome

## Evidence Register
Evidence ID | Date | Task ID | Evidence Type | Description | File Path | Result | Verified By | Notes

## Test Register
Test ID | Task ID | Test | Command | Expected | Actual | Status | Evidence

## Model Results
Model | Dataset | Target | Metrics | Run Date | Artifact | Status

## Dashboard
Metric | Value
total tasks | 17
completed | 5
in progress | 1
blocked | 0
not started | 11
total planned hours | 123
total recorded actual hours
evidence count | 0
test pass count | 0
test failure count | 0